2019 Annual Comprehensive Economic Development Strategy (CEDS)

And Progress Report

Grantee: 	Beartooth RC&D Area, Inc.

Project Number:  ED18DEN3020030

Period covered by the report:  Jan. 1, 2019 – Dec. 31, 2019

Adjustments: No significant adjustments were made to the strategy, program delivery or service area during this reporting period.  Steve Simonson has replaced Sue Taylor as Director of Economic Development for Beartooth R, C & D in February 2019.

Beartooth staff updated the website during 2019 (www.beartooth.org) and feel those changes will serve the region more effectively in the future. Beartooth staff and the Board President are working to post regular updates to the Facebook page and we continue efforts to be more proactive in marketing the organization and program areas. The Board of Directors approved additional funding from the State of Montana to the Food and Ag and Certified Regional Development Corporation programs. As reported last year, we continue to seek opportunities to further increase and diversify revenue sources in order to ensure a sustainable future and the ability to expand staffing levels as new programs to benefit the service area are identified.

We feel that our overall strategy is sound and aligned with the needs of the region, so no significant adjustments to the strategy has been implemented at this time. That being said, we also realize that there are opportunities for continued improvement to the strategies. The following paragraphs contain a summary of the CEDS Goals and Objectives, problems and opportunities along with comments regarding areas for improvement, where appropriate.

Infrastructure – This continues to be an area of high need throughout our region, the state and the nation and the costs to replace or upgrade is staggering. As Montana’s infrastructure continues to age, our smaller communities struggle to fund basic infrastructure needs. As a result of many conversations at the state and local levels, the Montana Infrastructure Coalition http://mtinfrastructure.org/ was established to provide an inclusive, non-partisan forum to research and develop funding solutions for Montana’s most pressing infrastructure needs. Beartooth monitors the activity and receives regular updates through our Montana Economic Developers Association membership and joined the infrastructure coalition in 2019.

- Water/Waste Water – All of our communities in the region are facing water and/or waste water needs. Absarokee Water & Sewer Districts will be seeking grants to complete improvements to its waste water system.  The City of Laurel may be seeking EDA funding to extend services to the new west-end interchange. Beartooth staff members are also assisting the Town of Joliet on improvements to their municipal water system.

- Housing – Meetings were held in each county regarding matters related to workforce housing. We continue to make a concerted effort to address the housing needs of households in the 80-120% of median household income throughout the region to ensure that our communities are in a better position to attract and retain those workers in that income demographic. During 2019, the Red Lodge Area Community Foundation’s Workforce Housing Committee made a housing unit available for low-to-moderate income workers. Work began on the land placed in the ownership of Trust Montana and the homes should be available for purchase in 2020.

- Detention Center - Beartooth staff is assisting the discussion for a three-county regional detention center being proposed for Carbon, Stillwater and Sweet Grass Counties.

- Solid Waste – In early October 2019, Beartooth R, C&D wrote a Delivering Local Assistance grant to reestablish solid waste service in Lodge Grass after a three year absence.

- Transportation – The City of Billings is continuing work on its transportation plan, including a bypass in the Heights west of the airport. A new interchange is being constructed on the west side of Laurel and work was mostly completed on an 11-mile stretch of Highway 212 between Laurel and Rockvale. Due to limited funding and actual cost overruns, only three of four lanes were finished. Montana Department of Transportation plans to complete the road in 2020. Roads were severely damaged in Stillwater County due to spring flooding. An application for funding assistance from EDA will be submitted spring 2020.

- Communication Infrastructure – Our region continues to improve connectivity to businesses and residents. However, this is an expensive undertaking by the telecommunication companies and financial resources are limited. All broadband and telecommunication companies in our region were contacted about the USDA Reconnect grant program. None of the companies acted upon this funding opportunity in our area. Beartooth continues to work with the communities and counties in our region to identify specific communication infrastructure needs and then identify potential solutions to those needs. One such solution may be the Mimosa or Motorola umbrella or canopy system that doesn’t require hard wiring and “last mile” connection costs to deliver high speed connectivity.

Economy – This CEDS goal remains at the core of our activities and we continue to improve the delivery and effectiveness of the technical assistance delivered by staff members. As usual, the greatest challenge associated with this goal is related to limited staff time for outreach and additional technical assistance. Overall, we experienced an increase in requests from the business sector and a slight decrease in requests from all other sectors combined.

Summary of highlights:

- NRCS/RCPP project is a multi-year collaborative research project involving irrigated barley and sugar beet producers to define production practices that will conserve water and soil and create more efficient agricultural operations. Beartooth has been invited to reapply for continued project funding in 2020. Beartooth is working with the Conservation Districts in Carbon, Big Horn and Yellowstone Counties.

- The Food and Ag Center has seen steady activity with value-added Ag projects topping the list. Smaller meat processing facilities continue to be an area of interest, but these are difficult to prove feasible in our smaller market.

  - Beartooth staff saw a significant decrease in the number of producers pursuing Growth Through Ag grant funding. The program underwent changes in 2017 to a single application cycle, along with a geographic shift in the location of Food and Ag Centers. This change in the grant funding cycle has reduced applications to the program.

  - Additional funding for the Beartooth Food and Ag Center was awarded in 2019.

- Bridger Senior Center was awarded $57,500 for repair of the 100-year-old building foundation as a result of a grant submitted by Beartooth on behalf of Carbon County. Work will begin in 2020.

- Riverfront Park Master Plan in Billings involved a state planning grant, matched by city funds to determine a logical redevelopment plan for a thirty-acre park located on the northern shore of the Yellowstone River.

- Yellowstone Valley Food Hub low-cost launch, market study and feasibility is a project initiated by the Yellowstone Valley Citizen’s Council aimed at developing a regional food hub benefiting area producers, institutions, and residents. The group has been working toward this goal for several years and has built a broad base of support.

- Bighorn Valley Health Center (BVHC) completed a Preliminary Architectural Report (PAR) to determine if their rapidly growing facility should be expanded on its current site, occupy a remodeled space nearby, or build a new facility to meet the needs of the area. Beartooth supported a successful CDBG application in 2019. The Health Center is located in Hardin, a medically underserved area. The PAR recommended solution was to build a new facility and the BVHC Board is formulating a plan to proceed with this recommendation.

- Old Roosevelt School project in Red Lodge was awarded by Montana Dept. of Commerce, and then rescinded a CDBG loan to help the Red Lodge Area Community Foundation repair and replace the HVAC system. Some of the local business community, citing unfair competition with main street businesses came forward after the award and protested the loan.

- Two successful Big Sky Trust Fund (BSTF) grants were returned to the state by Montana Silversmiths as a less aggressive expansion strategy required less financial assistance was adopted by the new management.

Communication – “We’re all in it together!” has been adopted by the Montana Economic Developer’s Association as our theme.

- As a whole, communication throughout the region continues to improve and Beartooth continues to promote collaboration, communication, and partnerships at every opportunity.

- Beartooth serves as the facilitator for a multi-county Custer-Gallatin Working Group that strives to improve collaboration and communication with entities impacted by the two state forests and to assist in the update of the Forest Plan.

- The Coal Country Coalition between the four development agencies and the core group continues to work towards solutions for our coal-impacted communities in the region and beyond.

- Beartooth has increased our visibility and opportunity to communicate to the governing bodies, businesses, and organizations in our service region.

- We continue to provide presentations to targeted groups in the region in order to promote our programs and services.

- Beartooth joined all five county Chambers of Commerce to increase visibility and tell our story more effectively.

Services – The Beartooth region includes many opportunities to improve the standard of living by upgrading community services and their facilities. We are fortunate to be working closely with many of local organizations who provide these services. We will continue to collaborate with these local public and private sector agencies to leverage available resources to improve standards of living throughout the region.

- Parks, playgrounds, and open space development continue to be important to our communities and we were able to assist the PTA in Red Lodge with a “Kaboom!” playground grant.

- Local food systems are another area with 2019 activity, which included the Billings South Side Grocery Store feasibility study. A summer youth food project continues as a result of the connectivity of people and resources in Pryor and supporting the marketplace for food vendors in Crow Agency.

- The Red Lodge Area Community Foundation continues to work toward workforce housing solutions with Beartooth serving on the steering committee for this activity. RDACF is also working on an upgraded transportation plan for Carbon County.

Natural Resources

- As noted above, we continue to work with issues affecting the coal industry.

- After 11 years in development, a wind farm is under construction by Pacific Corp in southern Carbon County. This 230-megawatt operation will be completed in late 2020. 12 additional wind farms are under review or exploration in Stillwater County. Beartooth has been in discussion with area colleges and training centers to reestablish a wind turbine operator program in the region.

- All five counties have representation by the Conservation Districts on the Board of Directors and we offer assistance to their work plans as needed, including the NRCS/RCPP project in Carbon, Big Horn, and Yellowstone Counties.

Human Capital

Within this goal, we most often partner with local economic development agencies as needed to improve the overall condition and opportunities for existing and potential employees, including access to training and education.

Board/CEDS Committee List:

EDD BOARD MEMBERSHIP ROSTER

Updated 12/20/2019

- GOVERNMENT REPRESENTATIVES   (51-65%)

Elected officials and/or employees of a general purpose unit of state, local or Indian tribal government who have been appointed to represent the government.

| Name | Government | Position |
| --- | --- | --- |
| Page Dringman Melanie Roe Chris Mehus Frank Ewalt Dan Lowe Don Jones Ty Hamilton (Open position) (Open position) Barb Wagner Clinton Giesick Pitts DeArmond Bill Foisy Clayton Greer Sidney Fitzpatrick | City of Big Timber Sweet Grass County Sweet Grass Cons. Dist. City of Billings Big Horn Cons. Dist. Yellowstone County Stillwater County Crow (Apsaalooke) Nation Stillwater County Yellowstone Conservation District Carbon Conservation District Carbon County City of Red Lodge City of Hardin Bighorn County | City Planner/Appointed by Big Timber City Council County Commissioner District Appointee City Council member Board Member-elected county position County Commissioner County Commissioner Director of Economic Development Economic Dev. Coor.-employee of Stillwater County Board Member-elected County position Board Member-elected County position County Commissioner City Council member City Council member County Commissioner |

- NON-GOVERNMENT REPRESENTATIVES   (35-49%)

- Private Sector Representatives: Any senior management official or executive, holding a key decision-making position, with respect to any for-profit enterprise. (At least one required)

| Name | Company / Enterprise | Position |
| --- | --- | --- |
| Liz Ching Randy Weamer Holly Higgins Marrisa Hauge | MT Dept. of Labor Sibanye-Stillwater Mine First Interstate Bank of Hardin Stillwater IGA | POWER grant administrator Public Affairs Manager/Appointed by CEO Branch Manager Manager of pharmaceutical sales |

- Stakeholder Organization Representatives: Executive directors of chambers of commerce, or representatives of institutions of post-secondary education, workforce development groups or labor groups. (At least one required)

| Name | Organization | Position |
| --- | --- | --- |
| (open position) Ryan Van Ballegooyen Jeffery McDowell | MSU-Billings College of Tech. Billings Job Service Hardin Chamber of Commerce /Two Rivers Authority | Project Manager – College of Technology Region 4 Director Past President / Executive Director |

- AT LARGE REPRSENTATIVES: Interested individuals qualified to provide input on behalf of their respective communities.

| Name | Company / Enterprise | Position |
| --- | --- | --- |
| (open position) Marvin Carter Lorene Hintz Emily Ringer | City of Columbus City of Laurel Big Sky EDA Town of Joliet | Appointed Representative for City of Columbus Appointed Representative for City of Laurel Small Business Development Center Appointed by the Town of Joliet |

CALCULATIONS

Number	Percent

- Government Representatives (51-65%)					 15	 52%

- Non- Government Representatives (35-49%)				  9	 33%

- Private Sector Representatives (at least 1)			 	  6

- Stakeholder Organization Representatives (at least 1)	 		  3

- At Large Representatives 							  4	 15%

Total Board Membership							 27	100%

EDD STRATEGY COMMITTEE ROSTER

Updated 12/20/19

NOTE:  This committee structure has been utilized by the organization since 1997 as a subset of the Board of Directors to discuss important issues and provide a representative perspective of the regional economy.

1. PRIVATE SECTOR REPRESENTATIVES   (At least 51%)

Any senior management official or executive holding a key decision-making position, with respect to any for-profit enterprise.

| Name | Company | Position |
| --- | --- | --- |
| Randy Weimer Monte Koch Charli Smith Holly Higgins Royce Njos Charlene Johnson | Sibanye/Stillwater Mine Opportunity Bank Sweet Grass Chamber First Interstate Bank Bank of Red Lodge Plenty Doors CDC | Community Engagement Director Branch President Executive Director Branch Manager Assistant Vice President Executive Director |

- REPRESENTATIVES OF OTHER ECONOMIC INTERESTS (No more than 49%)

Persons who provide additional representation of the main economic interests of the region. These may include, but are not limited to:  public officials, community leaders, and representatives of workforce development boards, institutions of higher education, minority and labor groups, and private individuals.

| Name | Area of Interest | Position |
| --- | --- | --- |
| Dianne Lehm Lee Ann Godfrey Liz Ching Jeffery McDowell Dena Johnson | BSEDA-Yellowstone County ED Stillwater County ED Power Grant/Job Training Economic Development Business Development | Community Outreach Director Economic Development Director MT Dept. of Labor Executive Director Director Small Business Dev. Center |

CALCULATIONS						 	Number		Percent

Private Sector Representatives (at least 51%)				6		 55%

Representatives of Other Economic Interests (no more than 49%)	 	5		 45%

Total Committee Membership						11		100%

Staff:

Beartooth RC&D / Economic Development District is a 51-year-old organization professionally staffed through funding provided by our local communities, counties, Conservation Districts, Montana Department of Agriculture, Montana Department of Commerce, and the US Dept. of Commerce EDA. By virtue of our time in business we provide excellent stability, continuity and capacity to the communities we serve. Our current staff includes three full-time positions.

Joel Bertolino serves as Executive Director and was hired in October 2007. He is the full-time Food and Ag Center Director. Prior to his time at Beartooth, he spent 7 years with USDA Farm Services Agency administering a variety of price support and emergency disaster programs as well as 6 years with Carbon County Historical Society as a Historic Preservation Officer. Joel holds a B.A. in Political Science/Public Administration from Montana State University – Bozeman and has spent his life assisting with the family cattle ranch north of Red Lodge, MT that he now operates.

Jillann Knutson serves the organization as the full-time Finance Director providing organizational finance support, financial assistance to small businesses, and staff support to our Revolving Loan Committee. She began working for Beartooth RC&D in June 2006 as the administrative assistant and was promoted to her current position in September 2009. Jillann has several years of administrative experience. She is a graduate from Rocky Mountain College with a B.S. in Business Administration.

Steve Simonson serves as the full-time Economic Development Director and began employment with Beartooth in February 2019. Steve has 13 years of experience in community and economic development through positions held in Colorado and previous work in Montana. Steve brings experience in providing small business support, including owning three businesses and also has nonprofit management, serving as executive director for two economic and community development organizations. Steve is the lead staff person for both the EDA program and Montana’s Certified Regional Development program. Steve holds a B.S. from Montana State University-Bozeman and is an Economic Development Finance Professional.

Report:

In the section below, we outline our specific scope of work items for 2019 derived from our CEDS Goals and Objectives as well as the level to which each objective was achieved. The Scope of Work and Implementation FY 2019 listed below provide a summary of our project activity and are intended to be used as a reference to this report.

Scope of Work and Implementation Methodology FY 2019 from CEDS 2019-2023

Goal:    Maintain Eligibility with EDA. Supply the EDA with timely information on plant and large                                          business closures and the number of employees affected.

- Submit semi-annual and year-end financial reports as required.

ACCOMPLISHMENTS ACHIEVED: We a submitted timely semi-annual SF-425 document and anticipate submitting a timely year-end SF-425 document.

QUANTIFY DELIVERABLES: We anticipate a timely submission of the GPRA report on or before January 30, 2020.

DIFFICULTIES ENCOUNTERED: None

- Monitor and report positive or negative economic trends impacting growth and development, grant writing, and public meeting facilitation, as appropriate.

ACCOMPLISHMENTS ACHIEVED: Beartooth ED staff facilitated business development works in Big Timber and Red Lodge. Beartooth staff facilitated workforce housing meetings across the region. Beartooth is also facilitating regional discussions related to a three-county detention center. Monitored and reported out on economic trends.

QUANTIFY DELIVERABLES: Final annual CEDS and progress report was submitted on January 10, 2019.

DIFFICULTIES ENCOUNTERED: The vast amount of reporting time required by grant funders reduces our effective time in the field to conduct our work. Our limited staff of 3 FTEs, also creates issues for project completion.

Goal Area:      Policy – Leadership – Capacity Building

Strategy:  Understand and be able to communicate to value and overall goals of public policy documents including, but not limited to the following:

- Growth Policy Plans

- Downtown Master Plans

- CIP

- Overall Economic Development Plan

- Zoning Ordinances

- Annexation Policies

- Housing Assessments

Strategy:  Promote assistance with citizen education and public meeting facilitation for the purpose of creation and/or revision of public policy documents, as appropriate.

Strategy:  Promote the integration of economic development activities with all appropriate local and regional plans, including sustainability, transportation, land use, housing, trails, etc.

Strategy:  Provide assistance to local governments in order to secure funding for the creation and/or revision of public policy documents, including grant writing as appropriate.

ACCOMPLISHMENTS ACHIEVED: Beartooth ED staff participated in meetings with the Laurel Urban Renewal Area, (LURA), and Town of Joliet CIP. Beartooth staff is currently assisting Carbon County with detention center planning.

QUALIFY DELIVERABLES: ED staff attended two meetings to assist in the urban renewal planning in Laurel. Beartooth staff assisted engineering firm in Joliet with Capital Improvement Plan. Staff attended seventeen meetings and helped facilitate detention center planning committee meetings.

DIFFICULTIES ENCOUNTERED: Some of these activities are outside staff areas of expertise and will require additional training and expertise related to Tax Increment Financing Districts, Urban Renewal Districts, and jail standards.

Goal 2:    Encourage the development and delivery of leadership initiatives, including volunteer-based programs

Strategy:  Support local and regional initiatives that nurture future community leaders in business, government, education, and nonprofit organizations.

Strategy:  Encourage and support community participation in MEDA’s community review program.

ACCOMPLISHMENTS ACHIEVED: Beartooth staff joined the Chambers of Commerce in all counties served. Beartooth staff promotes Leadership Montana and other local capacity building programs such as Leadership Billings.

QUALIFY DELIVERABLES: Beartooth joined five Chambers of Commerce in the region. Ten applicants were selected into the Leadership Montana program in 2019 from the region.

DIFFICULTIES ENCOUNTERED: None

Goal 3:    Develop and promote programs that lead to capacity building activities throughout the service region

Strategy:  Strengthen and enhance our ability to provide programs and services on a regional basis which augment local community efforts through coordination, facilitation and education in the following areas:

  - Revolving Loan Fund

  - Montana Certified Regional Development Corporation

  - Montana Food and Ag Center / Montana Cooperative Development Program

  - Montana Main Street Program

  - Business Expansion and Retention (BEAR) Program

  - Business Planning/Technical Assistance (with SBA and SBDC)

ACCOMPLISHMENTS ACHIEVED: These programs and funding sources provide our organization with operating expenses and funding resources for clients. We utilize these programs on an ongoing basis and we rely on these areas to accomplish our work plan and carry out our CEDS activities. The Billings BEAR program (rebranded as Rock 31) experienced new activity during 2019 and the Rural BEAR Program continues to serve clients in the region. Beartooth staff continues to be actively engaged throughout the region and we have been able to leverage each of these programs for the benefit of our clients, communities, and counties. We have enjoyed another successful year in all program areas as evidenced by the numbers of projects listed in our individual scope of work items below as well as the attached spreadsheet. We are actively serving on committees and assisting with projects of our partner organizations including: Big Sky EDA, Stillwater County Economic Development Committee, Crow Economic Development, Red Lodge Area Community Foundation, Beartooth Rural BEAR Team, Montana Economic Developers Working Groups (Resource Assessment, Renewable Energy).

QUANTIFY DELIVERABLES: As in previous reports, this scope of work item is listed to reflect the various state and federal programs, as well as committees and boards that we successfully participate on during the course of any given year. Thus the results in this section are brief and refer to our continued eligibility, while the actual projects are referenced below in individual scope of work items.

DIFFICULTIES ENCOUNTERED: None.

Strategy:   Continue to promote regional communication and awareness of economic development- related issues through bi-monthly Board of Directors meetings, press releases, regular updates of our website and Facebook page, Board/community reports, success stories, etc.

ACCOMPLISHMENTS ACHIEVED: Beartooth RC&D regularly updates its website (www.beartooth.org). We continue to utilize a variety of ways to deliver information throughout the district. Board of Directors meetings are held bi-monthly and each staff member provides project updates and each board member provides an update from their respective organization and community. Regular postings are made to the Beartooth Facebook page.

QUANTIFY DELIVERABLES: Beartooth staff made annual presentations in December to 5 service counties and 3 larger cities. These presentations included written and verbal updates for projects in their respective jurisdictions as well as organizational funding requests.

DIFFICULTIES ENCOUNTERED: None

Strategy:   Provide facilitation assistance to community projects through services offered such as project coordination, community organizing, and working as a liaison between stakeholder groups.

Strategy:   Assist economic development partners, as appropriate, with the completion of their projects through collaboration and leveraging resources.

ACCOMPLISHMENTS ACHIEVED: Increased assistance to Stillwater and Sweet Grass Counties in 2019.

QUALIFY DEVELERABLES: Both economic developers in Stillwater and Sweet Grass Counties resigned in 2019. Beartooth staff picked up additional responsibilities.

DIFFICULTIES ENCOUNTERED: Beartooth staff picked up additional responsibilities without adding staff. Stillwater ED continues to be unfilled.

Goal Area: Infrastructure Development

Goal 1: Support public and private sector entities in the completion of infrastructure projects, including broadband

Strategy:  Provide assistance with citizen education, communication and public meeting facilitation for the purpose of the completion of infrastructure projects.

Strategy:  Provide assistance to public and private sector entities in order to help them secure funding for the completion of infrastructure projects.

ACCOMPLISHMENTS ACHIEVED: Presented to all five counties in our service area, plus Billing, Laurel, and Hardin City Councils.

QUALIFY DELIVERABLES: During MOU presentation in December, all counties and communities were informed of projects and funding available to help them with infrastructure development. Additional meetings were held throughout the year as needed.

DIFFICULTIES ENCOUNTERED: None

Goal 2:  Support public and private sector entities in the development of commercial infrastructure

Strategy:  Assist in the assessment of commercial infrastructure needs, including industrial parks, downtown revitalization, commercial district revitalization, and shovel-ready sites.

Strategy:  Assist with the development, including feasibility, and potential implementation funding for identified commercial infrastructure needs.

Strategy:  When requested, assist in the identification, evaluation, and potential cleanup of Brownfields sites for the purpose of appropriate reuse.

ACCOMPLISHMENTS ACHIEVED: Joliet Main Street application submitted. Other projects initiated in 2019: Lockwood industrial park water expansion and the Columbus Brownfields cleanup of old hospital site, and an Opportunity Zone (OZ), meeting was held in Red Lodge.

QUALIFY DELIVERABLES: Joliet submitted an application for the Montana Main Street program. In August, an Opportunity Zone meeting was held to explain the program to interested business and city officials.

DIFFICULTIES ENCOUNTERED: Billings city officials blocked water expansion to Lockwood unless annexation occurs first. Montana Department of Commerce would like to meet with the town before resubmitting the application. A new mayor was elected in Joliet who does not support the Main Street grant application.

Goal 3:  Support public and private sector entities in the assessment and development of workforce housing

Strategy:  Continue to work with the Red Lodge Housing Committee to develop appropriate workforce housing solutions.

Strategy:  Provide technical assistance and facilitate planning efforts for other areas of the region who are exploring workforce housing options to assess needs, identify gaps, and develop a plan of action that encourages private investment in the development of new housing or redevelopment of existing housing stock to fill gaps in workforce housing.

Strategy: Continue to build relationships with housing resource partners and stay informed as to workforce housing activities taking place in Montana and other rural areas, including potential sources of funding for planning and project implementation.

Strategy:  Remain aware of the Montana Cooperative Development Center’s activities involving housing cooperatives as a potential option.

Strategy:  Monitor information from NaCo regarding affordable housing options being leveraged in other parts of the country, including “Housing as Part of a County’s ED Strategy” report.

ACCOMPLISHMENTS ACHIEVED: Attended MT Dept. of Commerce Housing meeting. Steve kept informed of MCDC and NaCo efforts in housing.

QUALIFY DELIVERABLES: Beartooth ED staff attended housing meetings on affordable housing/workforce housing, MCDC efforts and attended the NaCo meeting in Denver in conjunction with the EDA review in August.

DIFFICULTIES ENCOUNTERED: none

Goal Area: Workforce Development

Goal 1: Learn, understand, and address the needs of area employers and employees, including attraction and retention

Strategy:  Learn and stay informed as to the activities, priorities, and tools available from BillingsWorks, DOL, and assist employers throughout the region, especially Yellowstone County.

Strategy:  Determine the capacity for rural areas to support the creation of local workforce council, committee or program with local leadership, utilizing BillingsWorks as a model.

Strategy:  Continue to work with Sweet Grass County Chamber of Commerce’s volunteer-based economic development committee to develop their capacity and knowledge, especially in the area of workforce development.

Strategy:  Understand and incorporate underlying factors influencing workforce development, such as housing options and shortage of reliable, affordable childcare into planning and implementation activities.

ACCOMPLISHMENTS ACHIEVED: Attended BillingsWorks, Sweet Grass County Economic Development, and workforce meetings.

QUALIFY DELIVERABLES: In April, Beartooth ED staff attended BillingsWorks meeting known as “Better Off in Billings”. Beartooth ED staff held a meeting with MSU-Billings College of Technology on establishment of a wind turbine operator program. Beartooth ED staff discussed affordable housing and childcare at various meetings in the region. Beartooth ED staff facilitated workforce housing meeting in Big Timber and brought USDA Rural Development housing experts to meet with community members.

DIFFICULTIES ENCOUNTERED: None

Goal 2: Collaborate with regional stakeholders to increase the alignment of education, industry, and workforce development

Strategy:  Participate in working groups, meetings, and training opportunities to increase this alignment throughout the region, as appropriate.

Strategy:  Assist in identifying resources, including funding resources and existing programs that would allow for implementation of partnering agency’s work in this area.

ACCOMPLISHMENTS ACHIEVED: Beartooth ED staff continued discussions with Billings Job Service staff and resource providers.

QUALIFY DELIVERABLES: Beartooth ED staff held meetings with Sibanye/Stillwater Mine staff, POWER Grant Administrator, Liz Ching, Coal Country Coalition members on cooperative efforts ongoing across the region. Beartooth ED staff also attend DOL state training on workforce development.

DIFFICULTIES ENCOUNTERED: None

Goal 3: Support training and retraining programs to further develop and retain the existing and future regional workforce.

Strategy:  Assist Crow Tribe Housing Authority in the development of workforce training programs that would provide skilled trades’ workers to build update and rehabilitate housing within their jurisdiction.

Strategy:  Understand and educate local stakeholders as to the benefits of internship programs and work based learning options to increase workforce development options.

Strategy:  Continue to participate in the Business Expansion and Retention Initiatives, including the current BEAR program.

Strategy:  Continue to collaborate with the Department of Labor’s POWER grant to assist in the retraining and retention of coal-impacted workers, especially in Big Horn County and the Crow Reservation.

ACCOMPLISHMENTS ACHIEVED: Participated in the Lt. Governor’s Main Street program in Crow Agency where work force issues were discussed.

QUALIFY DELIVERABLES: In June, Beartooth staff participated in the Main Street meeting and offered ongoing assistance. Beartooth supported Plenty Doors CDC application to the Big Sky Trust Fund for developing a training program at Little Big Horn College on the Crow Reservation. A Delivering Local Assistance grant was submitted on behalf of the Town of Lodge Grass that would help with job creation. Beartooth also participated at the NorthWestern Energy meeting at the listening session held by the PSC.

DIFFICULTIES ENCOUNTERED: The Crow Tribe had laid off nearly 1000 workers in order to attempt to balance the tribal budget, including housing authority personnel. In addition coal layoffs continue as Colstrip Units 1 & 2 were shut down. The operators of the Spring Creek Mine declared bankruptcy and a new operator is working through permitting and bonding issues with the state. Trained electricians, carpenters, and pipefitters have declined to offer assistance / mentorship to fellow tribal members to build capacity and assist with expansion and rehabilitation of tribal housing. DOL requires a one-to-one match for apprentices which is difficult to come by with respect to trained and willing skilled laborers.

Goal Area: Quality of Life

Goal 1: Assist public and private sector entities in the planning and completion of strategic placemaking projects

Strategy:  Assist communities and organizations in understanding the importance of placemaking, including generational priority factors, and facilitate planning meetings, as appropriate.

Strategy:  Assist communities and organizations with the identification of resources to complete placemaking projects.

Goal 2: Assist public and private sector entities to achieve mutually beneficial natural resource development

Strategy:  Continue to support the development of renewable energy projects and monitor activity and progress in the region.

Strategy:  Continue to learn and understand concerns by units of government regarding development of renewable energy projects, especially view-shed concerns.

Strategy:  Continue to provide technical assistance and support to fuels mitigation initiatives, as appropriate.

Strategy:  Continue to collaborate on projects involving natural resource development and provide facilitation and liaison services, as appropriate.

ACCOMPLISHMENTS ACHIEVED: Beartooth ED staff worked with wind farm projects across region. Beartooth staff discussed view-shed objection with new county commissioners.

QUALIFY DELIVERABLES: 13 wind farms are either operating or in some phase of development in the region. Two television news interviews were given regarding the Pryor Mountain Wind farm in southern Carbon County. Public presentations were given to Big Sky Economic Development staff and boards as well as area service clubs. A wind working group was established for the Montana Economic Developers Association (MEDA) with direction and input from Beartooth ED staff.

DIFFICULTIES ENCOUNTERED: None.

Goal Area: Business Development

Goal 1: Provide technical assistance and mentorship to new and existing business

Strategy:  Continue partnerships with local SBDC, MT Dept. of Commerce, MMEC, local economic development specialists, the BEAR program, Job Service personnel, and local institutions of higher education.

Strategy:  Continue to support and enhance existing industry clusters through technical assistance, research, and leveraging available resources.

Strategy:  Continue to support and enhance existing primary industries, including tourism through technical assistance, research, and leveraging available resources.

Strategy:  Continue to serve agricultural-related businesses, and value added processing opportunities for locally grown crops, as one of the Montana Food and Ag Centers.

Strategy:  Continue to support cooperative business development in the region, including housing cooperative development.

ACCOMPLISHMENTS ACHIEVED: Attended meetings with SBDC, Montana Dept. of Commerce, MMEC, Big Sky EDA, College of Technology, and MSU-Billings.

QUALIFY DELIVERABLES: Beartooth ED staff assisted 35 new and existing businesses. All non-agricultural related businesses were referred to the SBDC. Some of the agricultural-related businesses were also referred based upon their need for technical assistance. Four businesses were referred to MMEC for manufacturing and engineering assistance. Four BEAR (now rebranded as ROCK 31) visits were completed, including three rural visits. Four cooperative development projects were started in 2019. Other businesses were also referred to Veteran Business Outreach Center, (VBOC).

Affordable housing meetings have taken place in all counties in the service region, which have included information on housing cooperatives.

Two meetings with the Sibanye/Stillwater Mine took place including a meeting to expand local sources of procurement of supplies and materials. This $1B business is currently purchasing $100M of products from our region.

Another industry cluster evolving is the wind farm sector. 12 new wind farms are under some phase of development in the region, mostly in Stillwater County. One is up and running, two more are in the ground-breaking stage. Others are being reviewed by the Montana Public Service Commission or county permitting review process. MSU-Billings College of Technology was approached about reestablishing a wind turbine operator program for new job emerging in the region.

Tourism resources have been shared on the Crow Reservation via Plenty Doors CDC that identified tourism as an economic driver that they want to enhance. Other priorities include renewable energy, business development and Ag-related industry development.

Six value added agricultural businesses are being developed and expanded.

DIFFICULTIES ENCOUNTERED: The amount of work in the renewable energy sector wasn’t anticipated by Beartooth. Early closures of coal fired power plants at Colstrip and the rapid reduction of coal mining and related jobs is also negatively impacting the region. Employees are being offered other energy related jobs at this time.

Goal 2: Provide access to capital and funding mechanisms, including a regional RLF, to qualified existing and new businesses

Strategy:  Continue to provide assistance that would lead to funding from the Beartooth RLF.

Strategy:  Continue to promote and market the RLF while making technical assistance visits and providing planning assistance to business clients.

Strategy:  Continue to expand the RLF by marketing its services to and cooperating with commercial bankers and chambers of commerce throughout the region.

Strategy:  Support partner initiatives, including the Rock 31 program, which would provide access to capital and funding mechanisms, including venture capital and angel network funding.

ACCOMPLISHMENTS ACHIEVED: Attended partner meetings, chamber of commerce, met with potential loan clients and Rock 31 presenters at $1 Million Cups presentations. Beartooth ED staff attended Early Stage MT meetings.

QUALIFY DELIVERABLES: Beartooth ED staff attended 15 Chamber of Commerce meetings in 2019. Meet with all 35 new and existing business clients to explain RLF and “gap” financing. Beartooth ED staff supported partner organizations in all five counties in the region.

DIFFICULTIES ENCOUNTERED None

Goal 3:  Support local and regional business recruitment and outreach activities

Strategy:  Collaborate and assist local economic development partners to recruit and develop businesses that want to locate in our region, as requested.

Strategy:  Assist partners in the development and distribution of recruitment materials, as appropriate.

ACCOMPLISHMENTS ACHIEVED: Opportunity Zones (OZ), meetings attend, facilitated and marketing materials developed. Beartooth ED staff partnered with local economic developers on business recruitment.

QUALIFY DELIVERABLES: Two opportunity zone prospectuses were developed for Crow Reservation and Red Lodge. Big Sky EDA has developed their own marketing materials for the Billings OZ. Attended NADC meeting on OZ in 2019. Beartooth ED staff served to review state-wide initiative through MEDA for contracting to bring OZ training to state.

DIFFICULTIES ENCOUNTERED: None

Goal Area:  Innovation & Entrepreneurship

Goal 1: Support local and regional activities that elevate entrepreneurship and   innovation

Strategy:  Participate in and leverage resources available the Big Sky Economic    Development’s Rock 31 program operated by the SBDC that provides concept to commercialization services for new and existing businesses in the region.

Strategy:  Support and promote activities that lead to economic diversification.

Strategy:  Support and participate in local and regional activities that enhance the Innovate Montana initiative during Innovate Week.

Goal 2:  Support local and regional activities. Including incentives, that increase      growth rate and revenue of area businesses

Strategy:  Continue to provide technical assistance that would lead to funding for clients engaging in planning activities such as feasibility studies, building expansion, and industrial growth.

Strategy:  Support local incentives designed to increase the growth rate and revenue of local and regional businesses, as appropriate.

Strategy:  Support industry focused on education and training developed by Beartooth or partner entities, including institutes of higher education and Rock 31.

Goal 3:  Support job creation, private investment attraction, and advances in technology that strengthen existing traded sectors

Strategy:  Support the Billings Library in the possible formation of a patent and trademark center to assist innovators and entrepreneurs in researching potential opportunities.

ACCOMPLISHMENTS ACHIEVED: Beartooth ED staff participated in Rock 31 programs. Meetings with regional businesses to help diversify the economy were held. Beartooth ED staff attended Innovate Montana presentations. Beartooth ED staff held meetings with potential clients on feasibility studies, industrial growth, and training.

QUALIFY DELIVERABLES: Beartooth staff attended and participated in two Rock 31 programs that led to providing technical assistance for energy efficiency improvements, and feasibility studies for business expansion. Local and State Innovate Montana presentations were attended by Beartooth ED staff.

DIFFICULTIES ENCOUNTERED: A grant to support the Billings Library project was not funded.

Goal Area:  Economic Growth & Resiliency

Goal 1:  Support and generate activities that will lead to an increase in the capacity 	and diversity of the regional economy to produce goods and services

Strategy:  Assist communities with the assessment, facilitation and planning efforts that    would lead to the development of an economic diversification plan, especially in those areas with heavy reliance on a single industry. See below

Strategy:  Assist communities in the implementation of an economic diversification plan, including the identification and securing resources.

Goal 2:  Engage the region in Steady-State incentives to bolster long-term                   economic durability see below

Strategy:  Encourage and participate in comprehensive planning efforts that include extensive community participation to define and embrace a collective vision for resilience.

Strategy:  Assist communities and partners with business planning initiatives that address resiliency and post-disruption recovery.

Strategy:  Assist communities with planning efforts to employ safe development practices in business districts, including awareness and mitigation strategies for floodplain-designated areas

Goal 3:  Engage the region’s networks in Responsive initiatives to collaborate on existing and potential future challenges

Strategy:  Support and assist communities and counties in their adoption or update of hazard mitigation plans, utilizing tools such as those found at http://readyandsafe.mt.gov/Emergency

Strategy:  Assist in establishing a process for regular communication, and updating of business community needs as they relate to disaster recovery, as appropriate.

Strategy:  Communicate with elected officials as to their disaster response plans and potential gaps that should be addressed as part of their overall recovery plan.

ACCOMPLISHMENTS ACHIEVED: Beartooth ED staff discussed disaster declarations with each county in the region. The wildland forest urban interface (WUI) project was monitored by staff.

QUALIFY DELIVERABLES: An EDA disaster recovery grant for Stillwater County is currently underway. A meeting and tour of impacted road areas to the Sibanye/Stillwater Mine was held with area representative Kirk Keysor. WUI was handed off to other service providers including US Forest Service, BLM, and Carbon County Fire as Beartooth staff retired and funding was no longer available to support the program.

DIFFICULTIES ENCOUNTERED: None